## Data
Task | Early Start Date |  | Late Start Date | Duration | Early End Date | Late End Date | Depends on | Dependencies ok?
DC-AC Inverter Design | 2014-01-20 | week1 |  | 2 | 2014-02-03 |  | Duty Cyle Driver (Firmware)
DC-AC Inverter BB & Test | 2014-02-03 | week3 |  | 2 | 2014-02-17 |  | Design | Yes
DC-DC StepDown Design | 2014-02-03 | week3 |  | 2 | 2014-02-17 |  | Microcontroller output capability
DC-DC StepDown BB & Test | 2014-02-17 | week5 |  | 2 | 2014-03-03 |  | Design
AC-DC Rectifying Design | 2014-02-17 | week5 |  | 1 | 2014-02-24
AC-DC Rectifying BB & Test | 2014-02-24 | week6 |  | 2 | 2014-03-10 |  | Design
AC-AC Step Down Order Test | 2014-02-17 | week5 |  | 2 | 2014-03-03
PCB Design and Order | 2014-02-24 | week6 |  | 3 | 2014-03-17 |  | ALL Hardware
Build PCB | 2014-03-17 | week9 |  | 1 | 2014-03-24
Duty Cycle Driver | 2014-01-20 | week1 |  | 2 | 2014-02-03
USB Driver | 2014-01-27 | week2 |  | 3 | 2014-02-17
GroBot API | 2014-01-20 | week1 |  | 4 | 2014-02-17
WiFi Driver | 2014-02-17 | week5 |  | 2 | 2014-03-03
Component Routines | 2014-03-03 | week7 |  | 1 | 2014-03-10
Shell of Pages | 2014-01-20 | week1 |  | 3 | 2014-02-10
USB | 2014-02-10 | week4 |  | 1 | 2014-02-17
WiFi Internet | 2014-02-24 | week6 |  | 2 | 2014-03-10
Data Transfer (integration) | 2014-03-10 | week8 |  | 1 | 2014-03-17 |  | GroBot API
Formulas:
Early End Date = [Early Start Date]+[Duration]*7
Early Start Date = [Early Start Date, row above]+[Duration, row above]*7

## original
Task | Start Date | Duration (in weeks) | End Date | Week 3 2/2 | Week 4 2/9 | Week 5 2/16 | Week 6 2/23 | Week 7 3/2 | Week 8 3/9 | Week 9 3/16 | Week 10 3/23 | Week 11 3/30 | Week 12 4/6
Order Basic Parts, Lights | 2014-02-02 | 1 | 2014-02-09
Design,Order Water/AIR Chan | 2014-02-02 | 2 | 2014-02-16
Design,Order LED/AUX Chan | 2014-02-09 | 2 | 2014-02-23
Design, Order Micro. Connect | 2014-02-02 | 2 | 2014-02-16
Test Water/AIR | 2014-02-16 | 1 | 2014-02-23
Test LED/AUX | 2014-02-23 | 2 | 2014-03-09
Test Microcontroller | 2014-02-16 | 2 | 2014-03-02
PCB Design and Order | 2014-02-16 | 3 | 2014-03-09
Build PCB | 2014-03-09 | 1 | 2014-03-16
Test PCB | 2014-03-09 | 2 | 2014-03-23
Duty Cycle Driver |  | 2 weeks | #VALUE!
Falimiarize with the CC3200 | 2014-02-03 | 2 | 2014-02-17
Auxilary Drivers | 2014-02-09 | 3 | 2014-03-02
GroBot API | 2014-02-03 | 4 | 2014-03-03
WiFi Driver | 2014-02-16 | 4 | 2014-03-16
Component Routines | 2014-03-02 | 3 | 2014-03-23
Set Up Basics for Website | 2014-02-03 | 1 | 2014-02-10
Front End HTML/JSP | 2014-02-09 | 4 | 2014-03-09
Servlet, Datastore, Java | 2014-02-16 | 3 | 2014-03-09
Data Transfer (integration) | 2014-03-09 | 1 | 2014-03-16
Design Implementation Plan | 2014-01-28 | 1 | 2014-02-04 | Complete
Testing and Evaluation Plan | 2014-02-03 | 4 | 2014-03-03
Oral Progress Report | 2014-02-23 | 3 | 2014-03-16
Demo | 2014-03-16 | 3 | 2014-04-06
Ryan |  |  |  | James
Felix |  |  |  | Matt
Jake |  |  |  | Conan
Whole Team
Hardware Group (Ryan, Felix, Jake)
Formulas:
End Date = [Start Date]+[Duration (in weeks)]*7

## oh shit
Task | Start Date | Duration (in weeks) | End Date | Week 7 3/2 | Week 8 3/9 | Week 9 3/16 | Week 10 3/23 | Week 11 3/30 | Week 12 4/6 | Week 13 4/13
Order Basic Parts, Lights | 2014-02-02 | 1 | 2014-02-09
Design,Order Water/AIR Chan | 2014-02-02 | 2 | 2014-02-16
Design,Order LED/AUX Chan | 2014-02-09 | 2 | 2014-02-23
Design, Order Micro. Connect | 2014-02-02 | 2 | 2014-02-16
Test Water/AIR | 2014-02-16 | 1 | 2014-02-23
Test LED/AUX | 2014-02-23 | 2 | 2014-03-09
Test Microcontroller | 2014-02-16 | 2 | 2014-03-02
PCB Design and Order | 2014-02-16 | 3 | 2014-03-09
Build PCB | 2014-03-09 | 1 | 2014-03-16
Test PCB | 2014-03-09 | 2 | 2014-03-23
Duty Cycle Driver |  | 2 weeks | #VALUE!
Falimiarize with the CC3200 | 2014-02-03 | 2 | 2014-02-17
Auxilary Drivers | 2014-02-09 | 3 | 2014-03-02
GroBot API | 2014-02-03 | 4 | 2014-03-03
WiFi Driver | 2014-02-16 | 4 | 2014-03-16
Component Routines | 2014-03-02 | 3 | 2014-03-23
Set Up Basics for Website | 2014-02-03 | 1 | 2014-02-10
Front End HTML/JSP | 2014-02-09 | 4 | 2014-03-09
Servlet, Datastore, Java | 2014-02-16 | 3 | 2014-03-09
Data Transfer (integration) | 2014-03-09 | 1 | 2014-03-16
Testing and Evaluation Plan | 2014-02-03 | 4 | 2014-03-03
Oral Progress Report | 2014-02-23 | 3 | 2014-03-16
Demo | 2014-03-16 | 3 | 2014-04-06
Ryan |  |  |  | James
Felix |  |  |  | Matt
Jake |  |  |  | Conan
Whole Team
Hardware Group (Ryan, Felix, Jake)
Formulas:
End Date = [Start Date]+[Duration (in weeks)]*7

## revised
https://github.com/gconan/GroBot_DesignFiles.git | Start Date | Duration (in weeks) | End Date | Week 7 3/2 | Week 8 3/9 | Week 9 3/16 | Week 10 3/23 | Week 11 3/30 | Week 12 4/6 | Week 13 4/13 | Week 14 4/20 | DEMO 4/29
Order Lights, Water Pumps, Sockets, Fuses | 2014-02-02 | 1 | 2014-02-09
Akinwande and Fred about PCB and soldering | 2014-02-02 | 1 | 2014-02-09
Test Water and Air w and w/o uC | 2014-02-09 | 2 | 2014-02-23
Order components for Buck | 2014-02-02 | 2 | 2014-02-16
PCB Design
PCB Order | 2014-02-16 | 1 | 2014-02-23
Testing and Integration | 2014-02-23 | 2 | 2014-03-09
GroBot.h File | 2014-02-09 | 3 | 2014-03-02
Tesing with Hardware
Channel Drivers | 2014-02-03 | 4 | 2014-03-03
Main.c:: event loop, init timers | 2014-02-16 | 4 | 2014-03-16
Testing with Website
Http Request | 2014-03-02 | 3 | 2014-03-23
Front End HTML/JSP | 2014-02-09 | 4 | 2014-03-09
Servlet, Datastore, Java | 2014-02-16 | 3 | 2014-03-09
Data Transfer (integration) | 2014-03-09 | 1 | 2014-03-16
Testing and Evaluation Plan | 2014-02-03 | 4 | 2014-03-03
Oral Progress Report | 2014-02-23 | 3 | 2014-03-16
Demo | 2014-03-16 | 3 | 2014-04-06
Ryan |  |  |  | James
Felix |  |  |  | Matt
Jake |  |  |  | Conan
Whole Team
Hardware Group (Ryan, Felix, Jake)
Formulas:
End Date = [Start Date]+[Duration (in weeks)]*7