## Data
Task | Early Start Date |  | Late Start Date | Duration | Early End Date | Late End Date | Depends on | Dependencies ok?
DC-AC Inverter Design | 2014-01-20 | week1 |  | 2 | 2014-02-03 |  | Duty Cyle Driver (Firmware)
DC-AC Inverter BB & Test | 2014-02-03 | week3 |  | 2 | 2014-02-17 |  | Design | Yes
DC-DC StepDown Design | 2014-02-03 | week3 |  | 2 | 2014-02-17 |  | Microcontroller output capability
DC-DC StepDown BB & Test | 2014-02-17 | week5 |  | 2 | 2014-03-03 |  | Design
AC-DC Rectifying Design | 2014-02-17 | week5 |  | 1 | 2014-02-24
AC-DC Rectifying BB & Test | 2014-02-24 | week6 |  | 2 | 2014-03-10 |  | Design
AC-AC Step Down Order Test | 2014-02-17 | week5 |  | 2 | 2014-03-03
PCB Design and Order | 2014-02-24 | week6 |  | 3 | 2014-03-17 |  | ALL Hardware
Build PCB | 2014-03-17 | week9 |  | 1 | 2014-03-24
Duty Cycle Driver | 2014-01-20 | week1 |  | 2 | 2014-02-03
USB Driver | 2014-01-27 | week2 |  | 3 | 2014-02-17
GroBot API | 2014-01-20 | week1 |  | 4 | 2014-02-17
WiFi Driver | 2014-02-17 | week5 |  | 2 | 2014-03-03
Component Routines | 2014-03-03 | week7 |  | 1 | 2014-03-10
Shell of Pages | 2014-01-20 | week1 |  | 3 | 2014-02-10
USB | 2014-02-10 | week4 |  | 1 | 2014-02-17
WiFi Internet | 2014-02-24 | week6 |  | 2 | 2014-03-10
Data Transfer (integration) | 2014-03-10 | week8 |  | 1 | 2014-03-17 |  | GroBot API
Formulas:
Early End Date = [Early Start Date]+[Duration]*7
Early Start Date = [Early Start Date, row above]+[Duration, row above]*7

## Sheet1
Task | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
DC-AC Inverter Design
DC-AC Inverter BB & Test
DC-DC StepDown Design
DC-DC StepDown BB & Test
AC-DC Rectifying Design
AC-DC Rectifying BB & Test
AC-AC Step Down Order Test
PCB Design and Order
Build PCB
Duty Cycle Driver
USB Driver
GroBot API
WiFi Driver
Component Routines
Set Up Basics for Website
Front End HTML/JSP
Servlet, Datastore, Java
Data Transfer (integration)
Design Implementation Plan
Testing and Evaluation Plan
Oral Progress Report
Demo
Ryan | James
Felix | Matt
Jake | Conan
Whole Team